## Dashboard
Project Name: | Contact List Testing Project
Delivery Date: | 2026-01-12
Release Number: | Version 1
Designed By: | Maryan Kassis, Mariam Abulail, Laith Faheem
Browsers:
Android Versions:
iOS Versions:
Total Number of Test Cases | 58
Number of Passed Test Cases: | 46
Number of Failed Test Cases: | 11
Environment: | Windows 10+ Windows 11

## RTM
requirment ID | Requirement Statement | Requirement Type | Requirement Description | Test Case ID | actual result | Bug ID | Test Case Status
R_2.1 | POST /users – Add User | Functional | Register user with valid data | TC001 | Created user successfully |  | Passed
|  |  | Register user without first name | TC002 | 400 Bad Request, firstName required |  | Passed
|  | Validation | Register user without last name | TC003 | 400 Bad Request, lastName required |  | Passed
|  |  | Register user with short password | TC004 | Password is shorter than the minimum allowed length 7 |  | Passed
|  |  | Register user with numeric-only password | TC005 | Created user successfully | B001 | Failed
|  |  | Register user without password | TC006 | 400 Bad Request, password required |  | Passed
|  |  | Register user without email | TC007 | 1.Status code is 400 Bad Request 2.Response body is returned with an error message 3.Error message contains:"Email address is already in use" | B002 | Failed
|  | Validation | Register user with invalid email | TC008 | 400 Bad Request, message appears "Email is invalid", |  | Passed
|  | Security | Register user with duplicated email | TC009 | 400 Bad Request, message appears "Email address is already in use" |  | Passed
|  | Validation | Verify that token is returned in response body after successful registration | TC010 | Created user successfully with vaild token |  | Passed
|  | Security | Register user with password containing trailing space | TC011 | User created successfully (201 Created) | B003 | Failed
|  | Validation | Register user with number at the beginning of first name | TC012 | User created successfully (201 Created) | B004 | Failed
|  |  | Register user with number at the beginning of last name | TC013 | User created successfully (201 Created) | B005 | Failed
|  |  | System accepts Arabic characters in password | TC014 | User created successfully (201 Created) | B006 | Failed
|  |  | Register user with firstName containing trailing space | TC015 | User created successfully (201 Created) | B007 | Failed
|  |  | Register user with lastName containing trailing space | TC016 | User created successfully (201 Created) | B008 | Failed
R_2.2 | GET /users/me - Get User Profile | Security | Get profile with valid token | TC017 | 1.Status code is 200 2.Response body appear correctly |  | Passed
|  | Security | Get profile without token | TC018 | 1. Status code is 401 2. Response body shows error |  | Passed
|  | Functional | Get profile with invaild token | TC019 | 1. Status code is 401 2. Response body shows error |  | Passed
|  | Validation | Get profile after logout | TC020 | 1.Status code is 401 Unauthorized 2. The response body contains error message "Please authenticate" |  | Passed
R_2.3 | PATCH /users/me – Update User | Security | User is logged in and has a valid token | TC021 | updated user successfully with 200 status code |  | Passed
|  |  | User is logged in and has a valid token | TC022 | As expected |  | Passed
|  |  | User is logged in | TC023 | As expected |  | Passed
|  |  | User is logged in | TC024 | As expected |  | Passed
|  |  | User is logged in | TC025 | As expected |  | Passed
|  |  | User is logged in and has a valid token | TC026 | Status code was 200 There was no error message | B009 | Failed
|  |  | User is logged in and has a valid token | TC027 | incorrect data type was accepted with 200 status code | B010 | Failed
|  |  | User is logged in and has a valid token | TC028 | No error message with status code 200 | B011 | Failed
|  |  | User is logged in and has a valid token | TC029 | As expected |  | Passed
R_2.4 | POST /users/logout – Log Out User | Functional / Positive | Log out with valid token | TC030 | As expected |  | Passed
|  | Negative / Security | Log out without token | TC031 | As expected |  | Passed
|  | Negative / Security | Log out with invalid token | TC032 | As expexted |  | Passed
|  | Negative / Security | Verify token is invalid after logout | TC033 | As expexted |  | Passed
|  | Negative / Security | Log out twice using same token | TC034 | As expexted |  | Passed
|  | Negative / Security | Log out with malformed Authorization header | TC035 | As expexted |  | Passed
|  | Negative / Security | Log out with Bearer keyword but empty token | TC036 | As expexted |  | Passed
|  | Functional / Positive | Log in after logout with same credentials | TC037 | As expexted |  | Passed
|  | Functional / Positive | Access protected endpoint with token before logout | TC038 | As expexted |  | Passed
|  | Negative / Security | Log out should not return sensitive data | TC039 | As expexted |  | Passed
R_2.5 |  | Functional / Positive | Log in with valid credentials | TC040 | As expected |  | Passed
| POST /users/login – Log In User | Functional / Positive | Verify token is returned after successful login | TC041 | As expected |  | Passed
|  | Negative / Functional | Log in with wrong password | TC042 | As expected |  | Passed
|  | Negative / Functional | Log in with unregistered email | TC043 | As expected |  | Passed
|  | Negative / Validation | Log in without email | TC044 | As expected |  | Passed
|  | Negative / Validation | Log in without password | TC045 | As expected |  | Passed
|  | Negative / Validation | Log in with empty email | TC046 | As expected |  | Passed
|  | Negative / Validation | Log in with empty password | TC047 | As expected |  | Passed
|  | Negative / Validation | Log in with invalid email format | TC048 | As expected |  | Passed
|  | Negative / Validation | Log in with email containing leading/trailing spaces | TC049 | System trimmed spaces with 200 status code and token response |  | Passed
|  | Negative / Validation | Log in with password containing trailing space | TC050 | As expected |  | Passed
|  | Negative / Functional | Log in using different letter case in email (case-sensitivity check) | TC051 | System treats email case-insensitive and gave response with status code 200 |  | Passed
|  | Negative / Validation | Log in with missing JSON body | TC052 | As expected |  | Passed
|  | Negative / Validation | Log in with wrong Content-Type | TC053 | As expected |  | Passed
R_2.6 | DELETE /users/me – Delete User | Security | Delete user with valid token | TC054 | As expected |  | Passed
|  | Security | Delete user without token | TC055 | As expected |  | Passed
|  | Security | Delete User with invalid token | TC056 | As expected |  | Passed
|  | Functional | Delete user already deleted | TC057 | As expected |  | Passed
|  | Security | Verify user cannot login after deletion | TC058 | As expected |  | Passed

## Test cases
Test Case ID | Summary | Preconditions | Test Data | Steps to Reproduce | Expected Result | Actual Result | Status | Req. ID | Bug. ID | Designed By | Tested BY | notes
TC001 | Register user with valid data |  | firstName=Mariam lastName=Abulail email=mariam_test_111@gmail.com password=!@#12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": "Abulail", "email":"mariam_test_111@gmail.com", "password": "!@#12345" } 6.Click Send | 1.Status code is 201 Created 2.User account is created successfully 3.Response contains a valid token | Created user successfully | Passed | 2026-02-01 |  | M.Abulail | M.Abulail
TC002 | Register user without first name |  | lastName=Abulail email=mariam_test_2@gmail.com password=!@#12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "lastName": "Abulail", "email":"mariam_test_2@gmail.com", "password": "!@#12345" } 6.Click Send | 1.Status code is 400 Bad Request 2.Response body is returned with an error message 3.Error message contains:"firstName" is required | 400 Bad Request, firstName required | Passed | 2026-02-01 |  | M.Abulail | M.Abulail
TC003 | Register user without last name |  | firstName=Mariam email=mariam_test_22@gmail.com password=!@#12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "email":"mariam_test_22@gmail.com", "password": "!@#12345" } 6.Click Send | 1.Status code is 400 Bad Request 2.Response body is returned with an error message 3.Error message contains:"lastName" is required | 400 Bad Request, lastName required | Passed | 2026-02-01 |  | M.Abulail | M.Abulail
TC004 | Register user with short password |  | firstName=Mariam lastName=Abulail email=mariam_test_3@gmail.com password=12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "lastName": "Abulail", "email":"mariam_test_3@gmail.com", "password": "12345" } 6.Click Send | 1.Status code is 400 Bad Request 2.Response body is returned with an error message 3.Error message contains:"password" is shorted | Password is shorter than the minimum allowed length 7 | Passed | 2026-02-01 |  | M.Abulail | M.Abulail
TC005 | Register user with numeric-only password |  | firstName=Mariam lastName=Abulail email=mariam_test_4@gmail.com password=12345678 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName":"Mariam" "lastName":"Abulail" "email":"mariam_test_4@gmail.com" "password':"12345678" } 6.Click Send | System should reject weak password | Created user successfully | Failed | 2026-02-01 | B001 | M.Abulail | M.Abulail
TC006 | Register user without password |  | firstName=Mariam lastName=Abulail email=mariam_test_5@gmail.com | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName":"Mariam", "lastName":"Abulail", "email":"mariam_test_5@gmail.com" } 6.Click Send | 1.Status code is 400 Bad Request 2.Response body is returned 3.Error message contains:Path `password` is required | 400 Bad Request, password required | Passed | 2026-02-01 |  | M.Abulail | M.Abulail
TC007 | Register user without email |  | firstName=Mariam lastName=Abulail password=!@#12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName":"Abulail", "password": "!@#12345" } 6.Click Send | 1.Status code is 400 Bad Request 2.Response body is returned with an error message 3.Error message contains:"email" is required | 1.Status code is 400 Bad Request 2.Response body is returned with an error message 3.Error message contains:"Email address is already in use" | Failed | 2026-02-01 | B002 | M.Abulail | M.Abulail
TC008 | Register user with invalid email |  | firstName=Mariam lastName=Abulail email=mariam_test_1gmail.com password=!@#12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": "Abulail", "email":"mariam_test_1gmail.com", "password": "!@#12345" } 6.Click Send | 1.Status code is 400 Bad Request 2.Response body is returned 3.Error message contains:Path `email` is invaild | 400 Bad Request, message appears "Email is invalid", | Passed | 2026-02-01 |  | M.Abulail | M.Abulail
TC009 | Register user with duplicated email |  | lastName=Abulail email=mariam_test_2@gmail.com password=!@#12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName":"Mariam", "lastName": "Abulail", "email":"mariam_test_2@gmail.com", "password": "!@#12345" } 6.Click Send | 1.Status code is 400 Bad Request 2.Response body is returned with an error message 3.Error message contains:Email already exists | 400 Bad Request, message appears "Email address is already in use" | Passed | 2026-02-01 |  | M.Abulail | M.Abulail
TC010 | Verify that token is returned in response body after successful registration |  | firstName=Mariam lastName=Abulail email=mariam_test_77@gmail.com password=!@#12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": "Abulail", "email":"mariam_test_77@gmail.com", "password": "!@#12345" } 6.Click Send 7.Observe the response body | 1.Status code is 201 Created 2.User account is created successfully 3.Response contain a valid token | Created user successfully with vaild token | Passed | 2026-02-01 |  | M.Abulail | M.Abulail
TC011 | Register user with password containing trailing space |  | firstName = Mariam lastName = Abulail email = mariam_test_space@gmail.com password = "##123456758 " | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": "Abulail", "email": "mariam_test_space@gmail.com", "password": "##123456758 " } 6.Click Send 7.Observe the response body | 1.System should reject the password or trim the spaces 2.Status code should be 400 Bad Request 3.Error message should be returned | User created successfully (201 Created) | Failed | 2026-02-01 | B003 | M.Abulail | M.Abulail
TC012 | Register user with number at the beginning of first name |  | firstName = 1Mariam lastName = Abulail email = mariam_test_numFN@gmail.com password = !@#12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "1Mariam", "lastName": "Abulail", "email": "mariam_test_numFN@gmail.com", "password": "!@#12345" } 6.Click Send 7.Observe the response body | 1.System should reject invalid name 2.Status code should be 400 Bad Request 3.Error message should be returned | User created successfully (201 Created) | Failed | 2026-02-01 | B004 | M.Abulail | M.Abulail
TC013 | Register user with number at the beginning of last name |  | firstName = Mariam lastName = 1Abulail email = mariam_test_numLN@gmail.com password = !@#12345 | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": "1Abulail", "email": "mariam_test_numLN@gmail.com", "password": "!@#12345" } 6.Click Send 7.Observe the response body | 1.System should reject invalid name 2.Status code should be 400 Bad Request 3.Error message should be returned | User created successfully (201 Created) | Failed | 2026-02-01 | B005 | M.Abulail | M.Abulail
TC014 | System accepts Arabic characters in password |  | "firstName": "Mariam", "lastName": "Abulail", "email":"mariam_test_acceptedArabic@gmail.com", "password": "تقبل العربي " | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": "Abulail", "email":"mariam_test_acceptedArabic@gmail.com", "password": "تقبل العربي " } 6.Click Send | System should reject non-English characters in password | User created successfully (201 Created) | Failed | 2026-02-01 | B006 | M.Abulail | M.Abulail
TC015 | Register user with firstName containing trailing space |  | firstName = " Mariam" lastName = Abulail email = mariam_test_space@gmail.com password = "##123456758 " | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": " Mariam", "lastName": "Abulail", "email": "mariam_test_spaceFN@gmail.com", "password": "##123456758 " } 6.Click Send 7.Observe the response body | 1.System should reject the first name or trim the spaces 2.Status code should be 400 Bad Request 3.Error message should be returned | User created successfully (201 Created) | Failed | 2026-02-01 | B007 | M.Abulail | M.Abulail
TC016 | Register user with lastName containing trailing space |  | firstName = "Mariam" lastName = " Abulail" email = mariam_test_space@gmail.com password = "##123456758 " | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": " Abulail", "email": "mariam_test_spaceLN@gmail.com", "password": "##123456758 " } 6.Click Send 7.Observe the response body | 1.System should reject the last name or trim the spaces 2.Status code should be 400 Bad Request 3.Error message should be returned | User created successfully (201 Created) | Failed | 2026-02-01 | B008 | M.Abulail | M.Abulail
[10 empty] | M.Abulail | M.Abulail
TC017 | Get profile with valid token | User login or register | Vaild token | 1.Open Postman 2.Create a GET request 3.Enter URL:{{baseurl}}/users/me 4.Open Header 5.Put Authorization to be Bearer {{token}} 6.Click Send | 1.Status code is 200 ok 2.User inforamtion display | 1.Status code is 200 2.Response body appear correctly | Passed | 2026-02-02 |  | M.Abulail | M.Abulail
TC018 | Get profile without token | User login or register |  | 1.Open Postman 2.Create a GET request 3.Enter URL:{{baseurl}}/users/me 4.Click Send | 1. Status code is 401 Unauthorized 2. Response body contains error message like "No token provided" | 1. Status code is 401 2. Response body shows error | Passed | 2026-02-02 |  | M.Abulail | M.Abulail
TC019 | Get profile with invaild token | User login or register | invaild token | 1.Open Postman 2.Create a GET request 3.Enter URL:{{baseurl}}/users/me 4.Open Header 5.Put Authorization to be Bearer 1234 6.Click Send | 1. Status code is 401 Unauthorized 2. Response body contains error message like "No token provided" | 1. Status code is 401 2. Response body shows error | Passed | 2026-02-02 |  | M.Abulail | M.Abulail
TC020 | Get profile after logout | User logged in and logged out | Token from login | 1. Login and save token 2. POST /users/logout with token 3. GET /users/me with same token | 1. Status code is 401 Unauthorized 2. Response contains error message "Token is invalid" | 1.Status code is 401 Unauthorized 2. The response body contains error message "Please authenticate" | Passed | 2026-02-02 |  | M.Abulail | M.Abulail
TC021 | Update user with valid data | User is logged in and has a valid token | firstName: Maryan lastName:Kassis | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter payload 4. Press send | 1. Status code 200 OK 2. User details updated successfully 3. response contains updated firstName and lastName | updated user successfully with 200 status code | Passed | 2026-02-03 |  | M.Kassis | M.Kassis
TC022 | Update only one field | User is logged in and has a valid token | firstName: Dareen | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter payload 4. Press send | 1. Status code 200 OK 2. User firstName updated successfully 3. Other fields remain unchanged | As expected | Passed | 2026-02-03 |  | M.Kassis | M.Kassis
TC023 | Update user with valid token | User is logged in | valid token | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter header authorization token 3. Enter payload 4. Press send | 1. Status code 200 OK 2. Updated is allowed | As expected | Passed | 2026-02-03 |  | M.Kassis | M.Kassis
TC024 | Update user without token | User is logged in |  | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter payload 4. Press send | 1. status code 401 Unauthorized 2. Error message returned | As expected | Passed | 2026-02-03 |  | M.Kassis | M.Kassis
TC025 | Update user with invalid token | User is logged in | invalid token | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter header authorization token 3. Enter payload 4. Press send | 1. status code 401 Unauthorized 2. Error message returned | As expected | Passed | 2026-02-03 |  | M.Kassis | M.Kassis
TC026 | Update with empty request body | User is logged in and has a valid token |  | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Press send | 1. Status code 400 Bad request 2. Validation error message | Status code was 200 There was no error message | Failed | 2026-02-03 | B009 | M.Kassis | M.Kassis
TC027 | Update with invalid data type | User is logged in and has a valid token | firstName:12345 | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter payload 4. Press send | 1. Status code 400 Bad request | incorrect data type was accepted with 200 status code | Failed | 2026-02-03 | B010 | M.Kassis | M.Kassis
TC028 | Update with unexpected field | User is logged in and has a valid token | userName: Alex | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter payload 4. Press send | 1. Status code 400 Bad request 2. Field should be rejected | No error message with status code 200 | Failed | 2026-02-03 | B011 | M.Kassis | M.Kassis
TC029 | Verify update response structure | User is logged in and has a valid token | firstName: Maryan lastName:Kassis | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter payload 4. Press send | 1. Response is in JSON format 2. firstName , lastName | As expected | Passed | 2026-02-03 |  | M.Kassis | M.Kassis
TC030 | Log out with valid token | User logged in and token saved | Bearer token={{token}} | 1.Log in and save token 2.Create POST request 3.URL:{{baseUrl}}/users/logout 4.Header: Authorization=Bearer {{token}} 5.Send | 1.Status code is 200 OK 2.No response body OR success message (per API) 3.Token becomes invalid after logout | As expected | Passed | 2026-02-04 |  | laith
TC031 | Log out without token | User logged in (optional) |  | 1.POST {{baseUrl}}/users/logout 2.Do not send Authorization header 3.Send | 1.Status code is 401 Unauthorized 2.Error message like "No token provided"/"Please authenticate" | As expected | Passed | 2026-02-04 |  | laith | M.Abulail
TC032 | Log out with invalid token | None or user logged in | Authorization=Bearer 1234 | 1.POST {{baseUrl}}/users/logout 2.Header: Authorization=Bearer 1234 3.Send | 1.Status code is 401 Unauthorized 2.Error message indicates invalid token | As expexted | Passed | 2026-02-04 |  | laith | M.Abulail
TC033 | Verify token is invalid after logout | User logged in and logged out | Token from login | 1.Login → save token 2.POST /users/logout with token 3.GET {{baseUrl}}/users/me with same token | 1./users/me returns 401 Unauthorized 2.Message indicates token invalid / please authenticate | As expexted | Passed | 2026-02-04 |  | laith | M.Abulail
TC034 | Log out twice using same token | User logged in and logged out once | Token from login | 1.Login → save token 2.POST /users/logout (200 OK) 3.POST /users/logout again with same token | 1.Second logout should return 401 Unauthorized (token invalid) OR 2.200 OK but indicates already logged out (depends on API) | As expexted | Passed | 2026-02-04 |  | laith | M.Abulail
TC035 | Log out with malformed Authorization header | User logged in and token saved | Authorization=tokenOnlyWithoutBearer | 1.POST {{baseUrl}}/users/logout 2.Header: Authorization={{token}} (without Bearer) 3.Send | 1.Status code 401 Unauthorized 2.Error message indicates invalid authorization format/token | As expexted | Passed | 2026-02-04 |  | laith | M.Abulail
TC036 | Log out with Bearer keyword but empty token | User logged in (optional) | Authorization=Bearer | 1.POST {{baseUrl}}/users/logout 2.Header: Authorization=Bearer (no token) 3.Send | 1.Status code 401 Unauthorized 2.Error message indicates missing token | As expexted | Passed | 2026-02-04 |  | laith | M.Abulail
TC037 | Log in after logout with same credentials | User registered + previously logged out | email=test2fake.com password=myNewPassword | 1.Login → get token 2.Logout 3.Login again with same credentials | 1.Second login succeeds (200 OK) 2.New token returned (preferably different from previous) | As expexted | Passed | 2026-02-04 |  | laith | M.Abulail
TC038 | Access protected endpoint with token before logout | User logged in and token saved | Bearer token={{token}} | 1.Login → save token 2.GET {{baseUrl}}/users/me with token | 1.Status code 200 OK 2.Profile returned correctly | As expexted | Passed | 2026-02-04 |  | laith | M.Abulail
TC039 | Log out should not return sensitive data | User logged in | Token from login | 1.POST {{baseUrl}}/users/logout with valid token 2.Check response headers/body | 1.No token returned 2.No user password returned 3.No sensitive info exposed | As expexted | Passed | 2026-02-04 |  | laith | M.Abulail
TC040 | Log in with valid credentials | User is registered (active account) | email=test2fake.com password=myNewPassword | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users/login 4.Go to Body → raw → JSON 5.Enter: { "email":"test2fake.com", "password":"myNewPassword" } 6.Click Send | 1.Status code is 200 OK 2.Response contains a valid token 3.Response contains user info (if supported) 4.Password is NOT returned in response | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC041 | Verify token is returned after successful login | User is registered | email=test2fake.com password=myNewPassword | 1.POST {{baseUrl}}/users/login with valid credentials 2.Observe response body | 1.Token field exists 2.Token is not empty/null 3.Token format looks like JWT (3 parts separated by '.') | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC042 | Log in with wrong password | User is registered | email=test2fake.com password=WrongPass123 | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"test2fake.com", "password":"WrongPass123" } 3.Send | 1.Status code is 400/401 (per API design) 2.Error message indicates invalid credentials 3.No token returned | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC043 | Log in with unregistered email | None | email=notexist_123@test.com password=AnyPass123 | 1.POST {{baseUrl}}/users/login 2.Body with unregistered email 3.Send | 1.Status code is 400/401 2.Error message indicates invalid credentials/user not found 3.No token returned | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC044 | Log in without email | None | password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body: { "password":"myNewPassword" } 3.Send | 1.Status code is 400 Bad Request 2.Error message indicates email is required | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC045 | Log in without password | None | email=test2fake.com | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"test2fake.com" } 3.Send | 1.Status code is 400 Bad Request 2.Error message indicates password is required | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC046 | Log in with empty email | None | email="" password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"", "password":"myNewPassword" } 3.Send | 1.Status code is 400 Bad Request 2.Validation error message returned | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC047 | Log in with empty password | None | email=test2fake.com password="" | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"test2fake.com", "password":"" } 3.Send | 1.Status code is 400 Bad Request 2.Validation error message returned | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC048 | Log in with invalid email format | None | email=test2fake.com@@ password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body with invalid email format 3.Send | 1.Status code is 400 Bad Request 2.Error message indicates invalid email format | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC049 | Log in with email containing leading/trailing spaces | User is registered | email=" test2fake.com " password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body: { "email":" test2fake.com ", "password":"myNewPassword" } 3.Send | 1.System should trim spaces OR reject input 2.If trimmed: 200 OK + token 3.If rejected: 400 + validation message | System trimmed spaces with 200 status code and token response | Passed | 2026-02-05 |  | laith | M.Kassis
TC050 | Log in with password containing trailing space | User is registered | email=test2fake.com password="myNewPassword " | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"test2fake.com", "password":"myNewPassword " } 3.Send | 1.Status code 400/401 (password mismatch) 2.Error message invalid credentials 3.No token returned | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC051 | Log in using different letter case in email (case-sensitivity check) | User is registered | email=TEST2FAKE.COM password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"TEST2FAKE.COM", "password":"myNewPassword" } 3.Send | 1.Preferably system treats email case-insensitive and logs in (200 OK) 2.If case-sensitive: 400/401 invalid credentials | System treats email case-insensitive and gave response with status code 200 | Passed | 2026-02-05 |  | laith | M.Kassis
TC052 | Log in with missing JSON body | None |  | 1.POST {{baseUrl}}/users/login 2.Set Content-Type: application/json 3.Send with empty body | 1.Status code is 400 Bad Request 2.Error message returned | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC053 | Log in with wrong Content-Type | None | email=test2fake.com password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Set Content-Type: text/plain 3.Send body as plain text | 1.Status code 415 Unsupported Media Type OR 400 Bad Request 2.Clear error message | As expected | Passed | 2026-02-05 |  | laith | M.Kassis
TC054 | Delete user with valid token | User exists and is logged in | valid token | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Enter header authorization token 4. Press send | 1. Status code 200 OK 2. User account deleted successfully | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis
TC055 | Delete user without token | User exists and is logged in |  | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Press send | 1. Status code 401 unauthorized | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis
TC056 | Delete User with invalid token | User exists and is logged in | invalid token | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Enter header authorization token 4. Press send | 1. Status code 401 unauthorized | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis
TC057 | Delete user already deleted | User is deleted |  | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Press send | 1. Status code 401 unauthorized or 404 Not found | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis
TC058 | Verify user cannot login after deletion | user is deleted |  | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Press send | 1. Status code 401 unauthorized 2. Login not allowed | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis
TC030 | Delete user with valid token | User exists and is logged in | valid token | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Enter header authorization token 4. Press send | 1. Status code 200 OK 2. User account deleted successfully | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis
| Delete user without token | User exists and is logged in |  | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Press send | 1. Status code 401 unauthorized | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis
TC031 | Delete User with invalid token | User exists and is logged in | invalid token | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Enter header authorization token 4. Press send | 1. Status code 401 unauthorized | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis
TC032 | Delete user already deleted | User is deleted |  | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Press send | 1. Status code 401 unauthorized or 404 Not found | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis
| Verify user cannot login after deletion | user is deleted |  | 1. Use DELETE HTML request 2. Enter environment and endpoint 3. Press send | 1. Status code 401 unauthorized 2. Login not allowed | As expected | Passed | 2026-02-06 |  | M.Kassis | M.Kassis |  | Pre-request Script | Tests Script | Automation Notes
TC0 | Log in with valid credentials | User is registered (active account) | email=test2fake.com password=myNewPassword | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users/login 4.Go to Body → raw → JSON 5.Enter: { "email":"test2fake.com", "password":"myNewPassword" } 6.Click Send | 1.Status code is 200 OK 2.Response contains a valid token 3.Response contains user info (if supported) 4.Password is NOT returned in response | As expected | Passed | 2026-02-05 |  | laith | M.Kassis |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is 200 OK", function () { pm.response.to.have.status(200); }); const jsonData = pm.response.json(); pm.test("Token is returned", function () { pm.expect(jsonData).to.have.property("token"); pm.expect(jsonData.token).to.be.a("string").and.not.be.empty; }); // Save token for subsequent requests pm.environment.set("token", jsonData.token); // Optional: save user info if returned if (jsonData.user && jsonData.user._id) pm.environment.set("userId", jsonData.user._id); if (jsonData.user && jsonData.user.email) pm.environment.set("userEmail", jsonData.user.email); // Security check pm.test("Password is not returned", function () { pm.expect(pm.response.text().toLowerCase()).to.not.include("password"); }); | Login request. Saves token to Environment variable 'token' for next requests.
| Verify token is returned after successful login | User is registered | email=test2fake.com password=myNewPassword | 1.POST {{baseUrl}}/users/login with valid credentials 2.Observe response body | 1.Token field exists 2.Token is not empty/null 3.Token format looks like JWT (3 parts separated by '.') | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | const jsonData = pm.response.json(); pm.test("Token exists and is not empty", function () { pm.expect(jsonData).to.have.property("token"); pm.expect(jsonData.token).to.be.a("string").and.not.be.empty; }); pm.test("Token looks like JWT (3 parts separated by '.')", function () { const parts = jsonData.token.split("."); pm.expect(parts.length).to.eql(3); }); | Can be part of the same Login tests (TC021) if you prefer.
| Log in with wrong password | User is registered | email=test2fake.com password=WrongPass123 | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"test2fake.com", "password":"WrongPass123" } 3.Send | 1.Status code is 400/401 (per API design) 2.Error message indicates invalid credentials 3.No token returned | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in with unregistered email | None | email=notexist_123@test.com password=AnyPass123 | 1.POST {{baseUrl}}/users/login 2.Body with unregistered email 3.Send | 1.Status code is 400/401 2.Error message indicates invalid credentials/user not found 3.No token returned | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in without email | None | password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body: { "password":"myNewPassword" } 3.Send | 1.Status code is 400 Bad Request 2.Error message indicates email is required | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in without password | None | email=test2fake.com | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"test2fake.com" } 3.Send | 1.Status code is 400 Bad Request 2.Error message indicates password is required | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in with empty email | None | email="" password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"", "password":"myNewPassword" } 3.Send | 1.Status code is 400 Bad Request 2.Validation error message returned | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in with empty password | None | email=test2fake.com password="" | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"test2fake.com", "password":"" } 3.Send | 1.Status code is 400 Bad Request 2.Validation error message returned | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in with invalid email format | None | email=test2fake.com@@ password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body with invalid email format 3.Send | 1.Status code is 400 Bad Request 2.Error message indicates invalid email format | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in with email containing leading/trailing spaces | User is registered | email=" test2fake.com " password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body: { "email":" test2fake.com ", "password":"myNewPassword" } 3.Send | 1.System should trim spaces OR reject input 2.If trimmed: 200 OK + token 3.If rejected: 400 + validation message | System trimmed spaces with 200 status code and token response | Passed | 2026-02-05 |  | laith |  | Good to detect trimming behavior | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in with password containing trailing space | User is registered | email=test2fake.com password="myNewPassword " | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"test2fake.com", "password":"myNewPassword " } 3.Send | 1.Status code 400/401 (password mismatch) 2.Error message invalid credentials 3.No token returned | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in using different letter case in email (case-sensitivity check) | User is registered | email=TEST2FAKE.COM password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Body: { "email":"TEST2FAKE.COM", "password":"myNewPassword" } 3.Send | 1.Preferably system treats email case-insensitive and logs in (200 OK) 2.If case-sensitive: 400/401 invalid credentials | System treats email case-insensitive and gave response with status code 200 | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in with missing JSON body | None |  | 1.POST {{baseUrl}}/users/login 2.Set Content-Type: application/json 3.Send with empty body | 1.Status code is 400 Bad Request 2.Error message returned | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log in with wrong Content-Type | None | email=test2fake.com password=myNewPassword | 1.POST {{baseUrl}}/users/login 2.Set Content-Type: text/plain 3.Send body as plain text | 1.Status code 415 Unsupported Media Type OR 400 Bad Request 2.Clear error message | As expected | Passed | 2026-02-05 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401,415)", function () { pm.expect([400,401,415]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Adjust expected status to match your API (400 vs 401 vs 415).
| Log out with valid token | User logged in and token saved | Bearer token={{token}} | 1.Log in and save token 2.Create POST request 3.URL:{{baseUrl}}/users/logout 4.Header: Authorization=Bearer {{token}} 5.Send | 1.Status code is 200 OK 2.No response body OR success message (per API) 3.Token becomes invalid after logout | As expected | Passed | 2026-02-02 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } // Ensure token exists before sending the request const token = pm.environment.get("token") ¦¦ pm.collectionVariables.get("token"); pm.expect(token, "token variable is missing. Run Login first.").to.not.be.undefined; pm.expect(token, "token variable is empty.").to.not.equal(""); | pm.test("Status code is 200 OK", function () { pm.response.to.have.status(200); }); // Optional: logout response should not include token/password pm.test("No sensitive data exposed", function () { const body = pm.response.text().toLowerCase(); pm.expect(body).to.not.include("token"); pm.expect(body).to.not.include("password"); }); // Clear token locally so next requests don't accidentally use it pm.environment.unset("token"); | Logout request. Requires token. Clears 'token' after success.
| Log out without token | User logged in (optional) |  | 1.POST {{baseUrl}}/users/logout 2.Do not send Authorization header 3.Send | 1.Status code is 401 Unauthorized 2.Error message like "No token provided"/"Please authenticate" | As expected | Passed | 2026-02-04 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401)", function () { pm.expect([400,401]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Negative logout tests. Make sure the Authorization header matches the case (missing/invalid/malformed).
| Log out with invalid token | None or user logged in | Authorization=Bearer 1234 | 1.POST {{baseUrl}}/users/logout 2.Header: Authorization=Bearer 1234 3.Send | 1.Status code is 401 Unauthorized 2.Error message indicates invalid token | As expexted | Passed | 2026-02-04 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401)", function () { pm.expect([400,401]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Negative logout tests. Make sure the Authorization header matches the case (missing/invalid/malformed).
| Verify token is invalid after logout | User logged in and logged out | Token from login | 1.Login → save token 2.POST /users/logout with token 3.GET {{baseUrl}}/users/me with same token | 1./users/me returns 401 Unauthorized 2.Message indicates token invalid / please authenticate | As expexted | Passed | 2026-02-04 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } // This request should use Authorization: Bearer {{oldToken}} const oldToken = pm.environment.get("oldToken") ¦¦ pm.collectionVariables.get("oldToken"); pm.expect(oldToken, "oldToken is missing. Save it before logout.").to.not.be.undefined; | pm.test("Status code is 401 Unauthorized", function () { pm.response.to.have.status(401); }); | Before running logout, save old token: pm.environment.set('oldToken', pm.environment.get('token')); then logout; then call /users/me with oldToken.
| Log out twice using same token | User logged in and logged out once | Token from login | 1.Login → save token 2.POST /users/logout (200 OK) 3.POST /users/logout again with same token | 1.Second logout should return 401 Unauthorized (token invalid) OR 2.200 OK but indicates already logged out (depends on API) | As expexted | Passed | 2026-02-04 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status indicates token invalid OR already logged out (API-dependent)", function () { pm.expect([200, 401]).to.include(pm.response.code); }); | Second logout behavior differs by implementation; 401 is common.
| Log out with malformed Authorization header | User logged in and token saved | Authorization=tokenOnlyWithoutBearer | 1.POST {{baseUrl}}/users/logout 2.Header: Authorization={{token}} (without Bearer) 3.Send | 1.Status code 401 Unauthorized 2.Error message indicates invalid authorization format/token | As expexted | Passed | 2026-02-04 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401)", function () { pm.expect([400,401]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Negative logout tests. Make sure the Authorization header matches the case (missing/invalid/malformed).
| Log out with Bearer keyword but empty token | User logged in (optional) | Authorization=Bearer | 1.POST {{baseUrl}}/users/logout 2.Header: Authorization=Bearer (no token) 3.Send | 1.Status code 401 Unauthorized 2.Error message indicates missing token | As expexted | Passed | 2026-02-04 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is one of expected (400,401)", function () { pm.expect([400,401]).to.include(pm.response.code); }); // Ensure token is NOT returned let hasToken = false; try { const jsonData = pm.response.json(); hasToken = !!jsonData.token; } catch (e) { // non-JSON error responses are acceptable } pm.test("No token returned", function () { pm.expect(hasToken).to.be.false; }); | Negative logout tests. Make sure the Authorization header matches the case (missing/invalid/malformed).
| Log in after logout with same credentials | User registered + previously logged out | email=test2fake.com password=myNewPassword | 1.Login → get token 2.Logout 3.Login again with same credentials | 1.Second login succeeds (200 OK) 2.New token returned (preferably different from previous) | As expexted | Passed | 2026-02-04 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } | pm.test("Status code is 200 OK", function () { pm.response.to.have.status(200); }); const jsonData = pm.response.json(); pm.test("Token is returned", function () { pm.expect(jsonData).to.have.property("token"); pm.expect(jsonData.token).to.be.a("string").and.not.be.empty; }); // Save token for subsequent requests pm.environment.set("token", jsonData.token); // Optional: save user info if returned if (jsonData.user && jsonData.user._id) pm.environment.set("userId", jsonData.user._id); if (jsonData.user && jsonData.user.email) pm.environment.set("userEmail", jsonData.user.email); // Security check pm.test("Password is not returned", function () { pm.expect(pm.response.text().toLowerCase()).to.not.include("password"); }); | Login again after logout; should succeed and return a token.
| Access protected endpoint with token before logout | User logged in and token saved | Bearer token={{token}} | 1.Login → save token 2.GET {{baseUrl}}/users/me with token | 1.Status code 200 OK 2.Profile returned correctly | As expexted | Passed | 2026-02-04 |  | laith |  | Use this as baseline before TC038 | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } // Ensure token exists before sending the request const token = pm.environment.get("token") ¦¦ pm.collectionVariables.get("token"); pm.expect(token, "token variable is missing. Run Login first.").to.not.be.undefined; pm.expect(token, "token variable is empty.").to.not.equal(""); | pm.test("Status code is 200 OK", function () { pm.response.to.have.status(200); }); pm.test("Response is JSON object", function () { const jsonData = pm.response.json(); pm.expect(jsonData).to.be.an("object"); }); | Baseline: verify token works before testing logout invalidation.
| Log out should not return sensitive data | User logged in | Token from login | 1.POST {{baseUrl}}/users/logout with valid token 2.Check response headers/body | 1.No token returned 2.No user password returned 3.No sensitive info exposed | As expexted | Passed | 2026-02-04 |  | laith |  |  | // Optional: ensure baseUrl exists if (!pm.environment.get("baseUrl") && !pm.collectionVariables.get("baseUrl")) { console.warn("baseUrl is not set. Add baseUrl to Environment or Collection Variables."); } // Ensure token exists before sending the request const token = pm.environment.get("token") ¦¦ pm.collectionVariables.get("token"); pm.expect(token, "token variable is missing. Run Login first.").to.not.be.undefined; pm.expect(token, "token variable is empty.").to.not.equal(""); | pm.test("Status code is 200 OK", function () { pm.response.to.have.status(200); }); pm.test("Logout response does not expose sensitive data", function () { const body = pm.response.text().toLowerCase(); pm.expect(body).to.not.include("password"); pm.expect(body).to.not.include("token"); }); | If your logout returns empty body, this should still pass.
Note on A1: بلزم نضيفم ولا فش داعي ؟ -Mariam Abulail

## Bug report
bug id | title | steps to reproduce | actual results | expected results | severity | priority | environment | screenshots | additional info:
B001 | Register user with numeric-only password | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName":"Mariam" "lastName":"Abulail" "email":"mariam_test_4@gmail.com" "password':"12345678" } 6.Click Send | User is created successfully (201 Created) | System should reject weak password and return validation error | High | High | OS: Windows 11 Tool: Postman API: Contact List App |  | TC019
B002 | Wrong validation message when email is missing during registration | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { { "firstName": "Mariam", "lastName": "Abulail", "password": "!@#12345" } 6.Click Send | Status 400, error message: "Email address is already in use" | Status 400, error message: "Email is required | Medium/High | Medium | OS: Windows 11 Tool: Postman API: Contact List App |  | TC021
B003 | System accepts password with trailing spaces during registration | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName":"Mariam" "lastName":"Abulail" "email":"mariam_test_space@gmail.com" "password':"12345678 " } 6.Click Send | 1.API returned 201 Created 2.User account was created successfully even though password had trailing spaces | 1.Status code should be 400 Bad Request 2.System should reject password with trailing spaces | Medium | High | "OS: Windows 11 Tool: Postman API: Contact List App" |  | TC025
B004 | User was created with number at the beginning of first name | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "1Mariam", "lastName": "Abulail", "email": "mariam_test_numFN@gmail.com", "password": "!@#12345" } 6.Click Send | User was created with number at the beginning of first name | Reject first name starting with number | Medium | High | "OS: Windows 11 Tool: Postman API: Contact List App" |  | TC026
B005 | User was created with number at the beginning of last name | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": "1Abulail", "email": "mariam_test_numLN@gmail.com", "password": "!@#12345" } 6.Click Send | User was created with number at the beginning of last name | Reject last name starting with number | Medium | High | "OS: Windows 11 Tool: Postman API: Contact List App" |  | TC027
B006 | System accepts Arabic characters in password | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": "Abulail", "email":"mariam_test_acceptedArabic@gmail.com", "password": "تقبل العربي " } 6.Click Send | User is created successfully (201 Created) | System should reject non-English characters in password | High | High | OS: Windows 11 Tool: Postman API: Contact List App |  | TC028
B007 | User firstName with leading spaces was auto-trimmed | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": " Mariam", "lastName": "Abulail", "email": "mariam_test_spaceFN@gmail.com", "password": "##123456758 " } 6.Click Send 7.Observe the response body | User created successfully (201 Created). Name stored as "Mariam" (spaces removed) without any error or warning | System should either: 1. Reject firstName with leading spaces (400 Bad Request) or 2. Trim the spaces and give a message indicating it was modified | Minor | Low | OS: Windows 11 Tool: Postman API: Contact List App |  | Trimming done automatically by system, but test expected either rejection or message
B008 | User lastName with leading spaces was auto-trimmed | 1.Open Postman 2.Create a POST request 3.Enter URL:{{baseUrl}}/users 4.Go to Body → select raw → choose JSON 5.Enter valid JSON body: { "firstName": "Mariam", "lastName": " Abulail", "email": "mariam_test_spaceLN@gmail.com", "password": "##123456758 " } 6.Click Send 7.Observe the response body | User created successfully (201 Created). Name stored as "Abbulail" (spaces removed) without any error or warning | System should either: 1. Reject lastName with leading spaces (400 Bad Request) or 2. Trim the spaces and give a message indicating it was modified | Minor | Low | OS: Windows 11 Tool: Postman API: Contact List App |  | TC030
B009 | Update with empty request body | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Press send | Status code was 200 There was no error message | 1. Status code 400 Bad request 2. Validation error message | Low | High | OS: Windows 10 Tool: Postman API: Contact List App
B010 | Update with invalid data type | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter payload 4. Press send | incorrect data type was accepted with 200 status code | 1. Status code 400 Bad request | medium | High | OS: Windows 10 Tool: Postman API: Contact List App
B011 | Update with unexpected field | 1. Use PATCH HTML request 2. Enter environment and endpoint 3. Enter payload 4. Press send | No error message with status code 200 | 1. Status code 400 Bad request 2. Field should be rejected | Low | High | OS: Windows 10 Tool: Postman API: Contact List App

## Test_Summary_report_new
Test summary report for Contact Listing APP
tested by | Maryan Kassis, Mariam Abulail, Laith Faheem
test date | 2026-11-01
Test name | Contact listing APP
test objective | Make sure Users APIs does not have critical bug
function | Description | TCs Executed | TCs Passed | TC failed | TCs Pending | Priority | Remarks
Add User | Create a new profile account | 16 | 8 | 8 | 0 | high
Get User Profile | Get the information of profile of any user | 4 | 4 | 0 | 0 | high
Update User | Update the profile informations | 9 | 6 | 3 | 0 | high
Log out User | Log out from the account | 10 | 10 | 0 | 0 | high
Log in User | Log in to the account | 14 | 14 | 0 | 0 | high
Delete User | Delete the account | 5 | 5 | 0 | 0 | high
|  | 58 | 47 | 11 | 0